## Boilerplate
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
26/07/2023 | Daily Standup

## Mehedi
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
2023-08-01 | PIL-291 | In Progress | 70% | 7 | Development | Career Page Form Validation with responsive.
2023-08-02 | PIL-291 | Done | 100% | 8 | Development | Career Page Form API Integration
2023-08-03 | PIL-295 | Done | 100% | 5 | Development | Fixed frontend design feedback
| PIL-288 | In Progress | 50% | 3 | Development | Admins & Mentors Add & Edit
2023-08-04 | PIL-288 | Done | 100% | 6 | Development | Admins & Mentors Add & Edit
| PIL-289 | In Progress |  | 1 | R & D | How can add subdomain in localhost
2023-08-07 | PIL_300 | In Progress | 60% | 7 | API Integration | Subdomain on Career page.
2023-08-08 | PIL-300 | Done | 100% | 8 | API Integration | Subdomain on Career page.
2023-08-09 | PIL-305 | Done | 100% | 4 | Setup | Laravel setup
2023-08-10 | PIL-308 | In Progress | 70% | 8 | POC | Connect with pusher in angular
2023-08-11 | PIL-308 | Done | 100% | 8 | POC | Connect with pusher in angular
2023-08-14 | On Leave
2023-08-16 | PIL-294 | In Progress | 30% | 8 | API Integration | Chating module
2023-08-17 | PIL-294 | In Progress | 80% | 8 | API Integration | Chating module
2023-08-18 | PIL-294 | Done | 100% | 8 | API Integration | Chating module
2023-08-21 | VUMI-345, VUMI-346, VUMI-347, VUMI-349 | Done | 100% | 8 | Development | VUMI CR
2023-08-22 | VMI-348, VUMI-350 | Done | 100% | 3 | Development | VUMI CR
| PIL-323 | In Progress | 70% | 5 | API Integration | Search user in chat module
2023-08-23 | PIL-324 | Done | 100% | 6 | API Integration | Search user in chat module
2023-08-24 | PIL-328 | Done | 100% | 8 | API Integration | Jobseekers API Integration
2023-08-25 | PIL-334 | Done | 100% | 8 | Bug & UI Fixing | Chating module
2023-08-28 | PIL-337 | Done | 100% | 6 | Static UI | Mentor Calendar
2023-08-29 | PIL-342 | Done | 100% | 8 | Static UI | Mentor Dashboard (Calendar & Sessions)
2023-08-30 | VUMI-357 | Done | 60% | 5 | Modify Code | Course Details Page

## Tarekul
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
2023-08-01 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-286 | Done | 60% | 5 | R&D, Implementation | Middleware Wrting, Admin can Create Mentro/Admin API
| PIL-292 | Done | 50% | 3 | R&D | sslCommerz Integration Laravel
2023-08-02 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 50% | 1.5 | R&D, Demo Implementation | sslCommerz Integration Laravel
|  | Done |  | 3 | R&D | Docker Desktop Basics
| PIL-294 | Done |  | 3 | R&D | Realtime Chat using Laravel & Angular
2023-08-03 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-294 | Done |  |  | R&D | Realtime Chat using Laravel & Angular, Chatify
2023-08-04 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-294 | Done |  | 2 | R&D | Realtime Chat using Laravel & Angular, Pusher
| PIL-142 | Done | 100% | 4.5 | Implementation | download My Reasume
| PIL-298 | Done | 100% | 1 | Implementation | Sign in with Google Button in frontend
2023-08-07 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-272 | Done | 100% | 5 | Implementation | Jobseeker Favorite Job List
| PIL-272 | Done | 100% | 0.5 | Refactor | Favorite Job API
| PIL-299 | Done | 100% | 2 | Implementation | Pagination added in Mentors and Admins frontend
2023-08-08 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
|  | Done | 100% | 1 | Implementaiton | Loading Element in Mentor and Admin Page
|  | Done | 100% | 4 | Refactor and optimization | Favorite Jobs Iteration Issue
| PIL-302 | Done | 100% | 2.5 | R&D, Testing | SSL Commerz Integration Moodle Course Enrollment
2023-08-09 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-307 | Done | 100% | 4 | R&D, Test | SSL Commerz payment Gateway
| PIL-294 | Done | 100% | 1.5 | Test, Assists | Chatify Chating module installation
| PIL-306 | Done | 100% | 2 | Refactor, Implementation | Frontend/favorite jobs loading fixed
2023-08-10 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 2.5 | Design | Billing information Preview
| PIL-292 | Done | 100% | 2.5 | implementation | SslCommerz Integration in Pyramid Backend
| PIL-292 | Done | 100% | 2.5 | implementation | SslCommerz Integration in Pyramid Frontend
| PIL-292 | Done | 100% | 1 | Design | Payment Status Component
2023-08-11 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 3 | implementation | SslCommerz Integration in Pyramid Backend
| PIL-292 | Done | 80% | 3 | implementation | SslCommerz Integration in Pyramid Frontend
| PIL-292 | Done | 100% | 1.5 | Design | Payment Status Component
2023-08-14 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 7.5 | implementation | SslCommerz Integration in Pyramid Backend
2023-08-16 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 50% | 5 | R&D, Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-292 | Done | 50% | 2.5 | Refactor | SslCommerz Integration in Pyramid Backend
2023-08-17 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 5 | Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-292 | Done | 100% | 2.5 | Changes | SslCommerz Integration in Pyramid Backend
2023-08-18 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 4 | Changes, Migration | Employer to admins request cycle for CV bank access with filters
|  | Done | 100% | 0.5 | Testing | Frontend CV Access Requests in local
| PIL-320 | Done | 80% | 3 | Testing, Installation | SSLCommerz Payment Gateway In Moodle
| PIL-322 | Done | 80% | 2 | implementation | Chatting module: Search users (Job seekers and employer)
2023-08-22 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 2 | Refactor, Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-285 | Done | 100% | 5 | Implementation | Job Application Filters
| PIL-301 | Done | 80% | 3 | Implementation | API for Employer can filter job seeker
2023-08-23 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-301 | Done | 100% | 3 | Changes, Implementation | API for Employer can filter job seeker
| PIL-286 | Done | 100% | 1 | Changes, Implementation | API: Export all data or filtered data from backend in a csv file
|  | Done | 100% | 4 | Implementation | Search APIs for JobSeekers
2023-08-24 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
|  | Done | 100% | 2 | Implementation | Add 'gender' field in user update form and add 'years_of_experience' in jobseeker profile update form (Frontend)
| PIL-301 | Done | 100% |  | Test, Issue solve | Job Application Filter
| PIL-331 | Done | 40% |  | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
2023-08-25 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 70% | 6 | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
| PIL-312 | Done | 100% | 1.5 | Fixing | Fix Filter Card at 150% scalling
2023-08-28 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 4 | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
| PIL-301 | Done | 100% | 2 | Fixing | Jobseeker Shortlisted Filter issue
|  | Done | 100% | 1.5 | Extracting, Backup | Elearning23 Course Backup
2023-08-29 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 6 | Fixing, Testing | Frontend: fixed Pagination, loading issues
| PD-235 | Done | 100% | 2 | Backup | Course Backup
2023-08-30 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PD-235 | Done | 100% | 2 | Backup | eLearning23 Course Backup
| PIL-345 | Done | 100% | 2.5 | implementation | API: Get Completed Course Details By User ID
| PIL-331 | Done | 100% |  | Recording | JobSeeker Filter Presentation Loom Video
| PIL-331 | Done | 100% | 3.5 | Fixing, Changes | JobSeeker Filter Issue
2023-08-31 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-345 | Done | 100% | 2.5 | implementation | API: auth-token and ids issue
| PIL-331 | Done | 100% | 2.5 | Fixing, Changes | JobSeeker Filter Issue, Pagination
| PIL-331 | Done | 100% |  | Recording | JobSeeker Filter Presentation Loom Video
|  | Done | 100% | 3 | Implementation | Service API to get mentors info
2023-09-01 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 1 | Recording, Editing | JobSeeker Filter Presentation Loom Video
|  | Done | 100% | 3 | Implementation | Service API to get mentors info
| PD-235 | Done | 100% | 1 | Course Backup | eLearning23 Course Backup
| PIL-352 | Done | 20% | 3 | Test and Implement | Moodle Web Services

## Irfan
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
2023-08-09 | PIL-294 | Done | 80% | 5.5 | R&D | Chatting Functionality
| PIL-304 | In Progress | 20% | 2 | Task | Job Details api
2023-08-10 | PIL-294 | Done | 90% | 1 | R&D | Helping Team mate on integration chat api
| PIL-304 | In Progress | 20% | 5 | Task | Job Details api
| VUMI-326 | Done | 100%% | 2 | Demo
2023-08-11 | PIL-309 | In Progress | 20% | 2.5 | Task | Jobseeker Filtering
| PIL-304 | Done | 100% | 5 | Task | Job Details api
2023-08-14 | PIL-309 | In Progress | 90% | 5 | Task | Jobseeker Filtering
| PIL-310 | In Progress | 100% | 0.5 | Task | Payment Gateway
| VUMI-324 | Done | 100% | 1.5 | Demo | Demo
2023-08-16 | PIL-310 | Done | 100% | 7 | Task | Payment Gateway Integration
2023-08-17 | PIL-318 | Done | 100% | 7.33 | Task | UI of CV Bank for admin and employer
2023-08-18 | PIL-320 | In Progress | 70% | 9 | Task | Api of CV Bank for admin and employer
2023-08-21 | PIL-320 | Done | 100% | 7 | Task | Api of CV Bank for admin and employer
2023-08-22 | PIL-324 | In Progress | 50% | 3 | Task | Testing and fixing responsive UI of some pages
| PIL-309 | Done | 100% | 1.5 | Task | Adding status column in table fetching from api response
| PIL-258 | Done | 100% | 2.5 | Task | Job Unlocking api intergration along with UI changes
2023-08-23 | PIL-325 | Done | 100% | 5.5 | Task | Issue fixing listed by Shadman Bhai
| PIL-312 | In Progress | 25% | 3.5 | Task | Api: checking whether job ready or not, create job ready course
2023-08-24 | PIL-312 | In Progress | 70% | 7.5 | Task | Api: checking whether job ready or not, create job ready course
2023-08-25 | PIL-312 | Done | 100% | 8 | Task | Job Ready Programme Flow
2023-08-28 | PIL-338 | Done | 100% | 1.5 | Meeting | Client Demo
| PIL-336 | Done | 100%% | 4.5 | Task | UI Fixing
2023-08-29 | VUMI-354 | In Progress | 30% | 0.5 | Task | Vumi: R&D on payment bug
| PIL-343 | Done | 70% | 4 | Task | Courses for Jobseekers: Static UI
| PIL-88 | Done | 100% | 3 | Task | Worked on getting jobseekers through query parameters passed from cv access page [admin panel]
2023-08-30 | VUMI-356 | Done | 100% | 6 | Task | Fix consecutive video activity, UI modification
| PIL-343 | In Progress | 75% | 1 | Task | Discussion, blocker with backend issue
2023-08-31 | PIL-348 | Done | 100% | 3.25 | Task | Worked on UI of available time slots for mentor from admin dashboard, discussion with Shadman bhai
| PIL-343 | Done | 100% | 2.75 | Task | Integrated course list api for jobseekers
| PIL-351 | In Progress | 10% | 0.5 | Task | Setting ip environment file, discussion
2023-09-01 | PIL-351 | In Progress |  |  | Task

## Sinthia
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
2023-08-01 | [5 empty] | Sick Leave
2023-08-02 | PIL-285 | Done | 100% | 4h | Development
| L10 | Done |  | 1.5h | Meeting
| ERP Entry+ Case Study Followup | Done |  | 2h | Meeting
| PIL-283 | In Progress | 10% | 1h | Development | Chatting apis
2023-08-03 | PIL-283 | Done |  | 6h | Development | Chatting POC with chatify
| PIL-297 | In Progress | 20% | 2h | Development | Career PAges Sub domain
| ERP Entry + DS | Done |  | 0.5h | Entry
2023-08-04 | PIL-235 | Done | 100% | 4h | Development | Google Auth + Bug solve of OAUTH
| PIL-297 | Done | 100% | 2h | Development | Career PAges Sub domain
| ERP Entry + DS | Done |  | 0.5h | Entry
2023-08-07 | ERP Entry + DS | Done |  | 0.5h | Entry
| PIL-301 | In Progress | 20% |  | Development | API for Employer can filter job seeker
| PIL-272 | Done |  | 1h | Followup | Briffing Tarikul about the API paginatoin and testing the response
| VUMI-340 | Blocker | 50% | 4h | Configure | SMTP and Auth Accounts setup
2023-08-08 | ERP Entry + DS | Done |  | 0.5h | Entry
| PIL-301 | In Progress | 20% | 5h | Development | API for Employer can filter job seeker
| Bigblue meeting | Done |  | 2h | Meeting | migration related meeting
2023-08-14 | ERP Entry + DS | Done |  | 0.5h | Entry
| PIL-301 | In Progress |  |  | Development | API for Employer can filter job seeker
| Bigblue meeting | Done |  | 6h | Meeting and checking issues | migration related meeting
2023-08-16 | ERP Entry + DS + L10 | Done |  | 1.5h | Entry
| PIL-301 | In Progress |  |  | Development | API for Employer can filter job seeker
| Bigblue meeting | Done |  | 6h | Meeting and checking issues | migration related meeting

## Shadman
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker | Responsible | Extra
2023-08-01 | PIL-290 | Done | 100% | 1 | Meeting | Meeting with Ahnaf bhai regarding demo video of pyramid for Raisul Bhai | Sinthia
| PIL-293 | Done | 100% | 7 | Development | Frontend CSS Load Delay issue in pyramid | Shadman
2023-08-02 | PIL-292 | In Progress | 10% | 1 | Meeting | Follow up and R&D on payment gateway |  | PD-200 (1.5h) Block attendance plugin
| PIL-296 | Done | 100% | 4 | Development | Sub domain and SSL setup learning from Ahnaf bhai |  | PNCST-249 (1.5h) L10
2023-08-03 | PIL-283 | In Progress | 10% | 1 | Development | Chatting API chatify R&D | Shadman | PD-208 (Attendance plugin followup)
| PIL-287 | Done | 100% | 4 | Development | Admin can create admins and mentors | Shadman | VUMI-342 (CSS loading delay issue fixed)
| PIL-297 | In Progress | 10% | 1 | Meeting | Career page sub domain api | SInthia
2023-08-04 | PIL-283 | In Progress | 10% | 4 | R&D | Chatify API R&D | Shadman | PD-200 (Block Plugin Follow up) (2h)
PD-179 (Proctoring Pro API discussion) (2h)
2023-08-07 | On Leave
2023-08-08 | PIL-122 | Done | 100% | 1 | Development | Job seekers can choose highest marks for quiz | Shadman | PD-221 (Proctoring Pro Setup in new site) (1h)
| PIL-283 | In Progress | 15% | 2 | Development | Discussion with Prosanto for chatify API | Shadman
| PIL-300 | Done | 100% | 1 | Follow up | Career page | Mehedi
| PIL-302 | In Progress | 10% | 1 | Follow up | SSL Commerz payment gateway | Tarekul
| PIL-80 | Done | 100% | 2 | Development | Apply on company site feature and requirement analysis | Shadman
2023-08-09 | PIL-283 | In Progress | 30% | 2 | R&D | Backend Chatting APIs | Shadman | A meeting with client for proctoring pro
| PIL-292 | In Progress | 30% | 1 | Meeting | SSL Commerz payment gateway | Tarekul
| PIL-303 | Done | 100% | 4 | Development | API: Job application fee | Shadman
| PIL-304 | In Progress | 10% | 1 | Meeting | API Integration: Job application fee | Erfan
2023-08-10 | PIL-283 | In Progress | 40% | 2 | Development | Backend Chatting APIs (Discussion with Prosanto) | Shadman | PD-181 (Proctoring pro regarding token generation) (1h)
| PIL-301 | In Progress | 50% | 4 | Development | Job application filter API | Sinthia | VUMI-343 (Client Communication) (1h)
2023-08-11 | PIL-139 | In Progress | 5% | 1 | Development | Job ready program R&D | Shadman | VUMI-343 (CR Estimation) (2h)
| PIL-283 | In Progress | 50% | 2 | Follow up | Backend Chatting API Followup | Shadman
| PIL-301 | In Progress | 30% | 2 | Meeting | Employer can filter job seeker (Meeting) | SInthia
| PIL-307 | In Progress | 30% | 1 | Follow up | Payment gateway | Tarekul
2023-08-14 | PIL-283 | In Progress | 50% | 2 | Development | Test and merge chatify package in pyramid | Shadman | VUMI-343 (Loom video followup and review) (1h)
| PIL-307 | In Progress | 80% | 2 | Follow up | Test and discussion with Tarekul bhai regarding payment flow | Tarekul
| PIL-315 | In Progress | 10% | 3 | Development | API: Add job application status in applicants list in jobs dashboard | Shadman
2023-08-16 | PIL-294 | In Progress | 60% | 4 | Development | API Integration: chatting (Bug fix) | Mehedi | VUMI client meeting
| PIL-307 | In Progress | 80% | 2 | Development | Payment gateway | Tarekul
| PIL-314 | In Progress | 80% | 2 | Development | CV bank access request | Tarekul
2023-08-17 | PIL-294 | In Progress | 90% | 3 | Development | API Integration: chatting (Bug fix) | Mehedi
| PIL-307 | Done | 100% | 3 | Development | Payment gateway (Bug fix) | Tarekul
| PIL-315 | Done | 100% | 2 | Development | Application status in jobs dashboard | Prosanto
2023-08-18 | PIL-314 | Done | 100% | 2 | Development | Employer admin request - (Bug fix)
| PIL-319 | In Progress | 20% | 3 | Development | Update job application status (Initial R&D and service function inspection)
| PIL-321 | Done | 100% | 1 | Meeting | Client meeting regarding dashboard and design
| PIL-322 | In Progress | 20% | 1 | Follow up | Initial discussion of search users for chatting module
2023-08-20 | [7 empty] | VUMI-351 (4h) (Course sorting from API) VUMI-352 (2h) (Discount module update) VUMI-353 (2h) (Students list filter)
2023-08-21 | PIL-319 | In Progress | 40% | 1 | Follow up | Update job application status | Prosanto | BB-253 (4h) (Meeting and issues finding)
| PIL-322 | In Progress | 60% | 1 | Follow up | Search users in chatting module | Tarekul | VUMI-353 (2h) (User Report Plugin)
2023-08-22 | PIL-301 | In Progress | 50% | 2 | Follow up | Job seeker filter | Tarekul | VUMI-352 (2h) Soft delete option in discount module
| PIL-311 | In Progress | 40% | 2 | Follow up | APIs related to job ready program | Prosanto
| PIL-315 | In Progress | 90% | 2 | Development | Update job application status | Shadman
2023-08-23 | PIL-311 | Done | 100% | 2 | Development | APIs related to job ready program | Prosanto | VUMI-351 (2h) VUMI-353 (2h)
| PIL-319 | Done | 100% | 2 | Development | Update job application status (Bug Fix) | Shadman
2023-08-24 | PIL-150 | Done | 100% | 4 | Development | Job ready course flow | Shadman | PNCST - 290 (2h) L10 Meeting
| PIL-331 | In Progress | 50% | 1 | Follow up | Job seeker filter in job seeker report
2023-08-28 | PIL-312 | Done | 100% | 2 | Follow up | Job ready course flow issue | Erfan
| PIL-331 | Done | 100% | 1 | Follow up | Job seeker filter | Tarekul
| PIL-338 | Done | 100% | 5 | Meeting | Client demo prep | Shadman
2023-08-29 | PIL-345 | In Progress | 10% | 1 | Follow up | API: Get My PET | Tareukl | VUMI-355 (4h) CR Release meeting
| PIL-347 | In Progress | 50% | 3 | Development | DB Design for mentor session booking | Shadman
2023-08-30 | PIL-345 | Done | 100% | 1 | Follow up | API: Get My PET | Tareukl | VUMI-356 (1h) Follow up PNCST-306 (1.5h) L10 Meeting PD-220 (1.5h) Plugin submission review
| PIl-347 | Done | 100% | 3 | Development | DB Design for mentor session booking | Shadman
2023-08-31 | PIL-345 | Done | 100% | 1 | Follow up | API: Get My PET |  | PD-220 (3h)
| PIL-347 | Done | 100% | 2 | Development | DB Design for mentor session booking |  | PD-248 (2h)
2023-09-01 | PIL-352 | In Progress | 20% | 2 | Follow up | Mentor available slot CRUD API | Tarekul | PD-248 (4h) Proctoring release PD-225 (2h) BKash Release

## Prosanto
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker | Extra
31/08/2023 | PD-244 | Done | 100% | 1 | Presentation |  | Demo video describing the features of proctoring pro
| PD-254 | Done | 100% | 2 | Development |  | Proctoring: Promotional page update
| PD-220 | Done | 100% | 2 | Documentation |  | Added License.md and thirdpartylibs.xml file for previously developed plugin.
30/08/2023 | PD-244 | In Progress | 80% | 4 | Presentation |  | Demo video describing the features of proctoring pro
| PD-245 | In Progress | 80% | 4 | Development |  | Proctoring: Promotional page update
29/08/2023 | PD-239 | Done | 100% | 4 | Development |  | Enable copy to clipboard feature for session modal
| PD-242 | Done | 100% | 4 | Presentation |  | Loom video describing the BS service API usage
28/08/2023 | PD-239 | In Progress | 40% | 2 | Development |  | Enable copy to clipboard feature for session modal
| PROD-17 | Done | 100% | 6 | Development |  | proctoring pro report page change
25/08/2023 | PROD-17 | In Progress | 40% | 8 | Development |  | Work on proctoring pro report images
24/08/2023 | PIL-311 | Done | 100% | 4 | Testing | Test Job Ready Program flow API's after deployment using postman
| PD-237 | Done | 100% | 4 | Development |  | Replace proctoring pro session modal.
23/08/2023 | PIL-311 | In Progress | 80% | 4 | Development | Implemented report to show which user has completed, which job ready courses. | Test previously developed API's with Shadman Bhai
|  |  |  | 2 |  | Added delete API to delete job ready program and courses.
|  |  |  | 2 |  | Updated JobController to show job ready program and course at job details.
22/08/2023 | PIL-311 | In Progress | 60% | 1 | Development | Initial Meeting with Shadman Bhai about the implementation.
|  |  |  | 2 |  | Created Migration file to update existing job table to add relevant columns.
|  |  |  | 3 |  | Implemented required API to create job ready programs and job ready courses.
|  |  |  | 2 |  | Created API to add job applications to job ready program.
21/08/2023 | PIL-319 | Done | 100% | 8 | Development | Implemented methods in the service class to update job application status based on completed job apply conditions. Pyramid API: Search user by name | Bugfix: Auth plugin Sentry
18/08/2023 | PIL-315 | Done | 100% | 8 | Development | Implemented job application status update based on all job conditions.