## পত্রক1
Date | Issue | Status | Percentage | Time Spent (Hour) | Category | Description/Comments/Blocker
2023-08-01 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-286 | Done | 60% | 5 | R&D, Implementation | Middleware Wrting, Admin can Create Mentro/Admin API
| PIL-292 | Done | 50% | 3 | R&D | sslCommerz Integration Laravel
2023-08-02 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 50% | 1.5 | R&D, Demo Implementation | sslCommerz Integration Laravel
|  | Done |  | 3 | R&D | Docker Desktop Basics
| PIL-294 | Done |  | 3 | R&D | Realtime Chat using Laravel & Angular
2023-08-03 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-294 | Done |  |  | R&D | Realtime Chat using Laravel & Angular, Chatify
2023-08-04 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-294 | Done |  | 2 | R&D | Realtime Chat using Laravel & Angular, Pusher
| PIL-142 | Done | 100% | 4.5 | Implementation | download My Reasume
| PIL-298 | Done | 100% | 1 | Implementation | Sign in with Google Button in frontend
2023-08-07 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-272 | Done | 100% | 5 | Implementation | Jobseeker Favorite Job List
| PIL-272 | Done | 100% | 0.5 | Refactor | Favorite Job API
| PIL-299 | Done | 100% | 2 | Implementation | Pagination added in Mentors and Admins frontend
2023-08-08 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
|  | Done | 100% | 1 | Implementaiton | Loading Element in Mentor and Admin Page
|  | Done | 100% | 4 | Refactor and optimization | Favorite Jobs Iteration Issue
| PIL-302 | Done | 100% | 2.5 | R&D, Testing | SSL Commerz Integration Moodle Course Enrollment
2023-08-09 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-307 | Done | 100% | 4 | R&D, Test | SSL Commerz payment Gateway
| PIL-294 | Done | 100% | 1.5 | Test, Assists | Chatify Chating module installation
| PIL-306 | Done | 100% | 2 | Refactor, Implementation | Frontend/favorite jobs loading fixed
2023-08-10 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 2.5 | Design | Billing information Preview
| PIL-292 | Done | 100% | 2.5 | implementation | SslCommerz Integration in Pyramid Backend
| PIL-292 | Done | 100% | 2.5 | implementation | SslCommerz Integration in Pyramid Frontend
| PIL-292 | Done | 100% | 1 | Design | Payment Status Component
2023-08-11 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 3 | implementation | SslCommerz Integration in Pyramid Backend
| PIL-292 | Done | 80% | 3 | implementation | SslCommerz Integration in Pyramid Frontend
| PIL-292 | Done | 100% | 1.5 | Design | Payment Status Component
2023-08-14 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-292 | Done | 100% | 7.5 | implementation | SslCommerz Integration in Pyramid Backend
2023-08-16 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 50% | 5 | R&D, Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-292 | Done | 50% | 2.5 | Refactor | SslCommerz Integration in Pyramid Backend
2023-08-17 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 5 | Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-292 | Done | 100% | 2.5 | Changes | SslCommerz Integration in Pyramid Backend
2023-08-18 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 4 | Changes, Migration | Employer to admins request cycle for CV bank access with filters
|  | Done | 100% | 0.5 | Testing | Frontend CV Access Requests in local
| PIL-320 | Done | 80% | 3 | Testing, Installation | SSLCommerz Payment Gateway In Moodle
| PIL-322 | Done | 80% | 2 | implementation | Chatting module: Search users (Job seekers and employer)
2023-08-22 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-314 | Done | 100% | 2 | Refactor, Implementation | Employer to admins request cycle for CV bank access with filters
| PIL-285 | Done | 100% | 5 | Implementation | Job Application Filters
| PIL-301 | Done | 80% | 3 | Implementation | API for Employer can filter job seeker
2023-08-23 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-301 | Done | 100% | 3 | Changes, Implementation | API for Employer can filter job seeker
| PIL-286 | Done | 100% | 1 | Changes, Implementation | API: Export all data or filtered data from backend in a csv file
|  | Done | 100% | 4 | Implementation | Search APIs for JobSeekers
2023-08-24 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
|  | Done | 100% | 2 | Implementation | Add 'gender' field in user update form and add 'years_of_experience' in jobseeker profile update form (Frontend)
| PIL-301 | Done | 100% |  | Test, Issue solve | Job Application Filter
| PIL-331 | Done | 40% |  | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
2023-08-25 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 70% | 6 | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
| PIL-312 | Done | 100% | 1.5 | Fixing | Fix Filter Card at 150% scalling
2023-08-28 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 4 | Implementation | Job seeker filter in jobseekers list in admin panel and with export button (new API)(Frontend)
| PIL-301 | Done | 100% | 2 | Fixing | Jobseeker Shortlisted Filter issue
|  | Done | 100% | 1.5 | Extracting, Backup | Elearning23 Course Backup
2023-08-29 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 6 | Fixing, Testing | Frontend: fixed Pagination, loading issues
| PD-235 | Done | 100% | 2 | Backup | Course Backup
2023-08-30 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PD-235 | Done | 100% | 2 | Backup | eLearning23 Course Backup
| PIL-345 | Done | 100% | 2.5 | implementation | API: Get Completed Course Details By User ID
| PIL-331 | Done | 100% |  | Recording | JobSeeker Filter Presentation Loom Video
| PIL-331 | Done | 100% | 3.5 | Fixing, Changes | JobSeeker Filter Issue
2023-08-31 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-345 | Done | 100% | 2.5 | implementation | API: auth-token and ids issue
| PIL-331 | Done | 100% | 2.5 | Fixing, Changes | JobSeeker Filter Issue, Pagination
| PIL-331 | Done | 100% |  | Recording | JobSeeker Filter Presentation Loom Video
|  | Done | 100% | 3 | Implementation | Service API to get mentors info
2023-09-01 | Daily Standup | Done | 100% | 0.5 | Meeting | Daily Hurdle, Daily Standup (Pyramid)
| PIL-331 | Done | 100% | 1 | Recording, Editing | JobSeeker Filter Presentation Loom Video
|  | Done | 100% | 3 | Implementation | Service API to get mentors info
| PD-235 | Done | 100% | 1 | Course Backup | eLearning23 Course Backup
| PIL-352 | Done | 20% | 3 | Test and Implement | Moodle Web Services